## Sheet1
Logic Model & Monitoring and Evaluation Plan for The Lab
OVERALL AIM: HELPING YOUNG PEOPLE TO…. |  |  |  | 9
Outcome | Activities | Outputs | Indicators | Evidence | Date | Who? | Completed? | Actions necessary
1. To improve the standards of music delivery for children and young people | Practitioner Reflective Practice | Monthly reflective practice records | 1.a Learning, reflective practice and good practice shared from AudioActive In The Lab events is informing delivery | Monthly RP records/journal
| YP Focus Groups | 20 YP engaged in 4 Focus Groups | 1.b Young People's voice has an increasing influence in the ongoing development and delivery of the programme | Minutes from YP focus Group
| AA in the lab debriefs |  |  | Tutor and YP testimonials
| Evaluation actitivities |  |  | Photo & Video documentation
|  |  | 1.c Practitioners and Young People's perceptions that quality is increasing | Monthly RP records/journal
Tutor and YP testimonials inc. YP's evaluations
Photo & Video documentation
| Equipment Upgrade | Purchased & Installed: 3 x mac book pro software vocal booth condenser mic 3 x midi keyboards 1 x DJ Mixer 1 x NI Maschine | 1.d Improved equipment and resource offer at The Lab has enhanced the range of delivery options and subsequent activities on offer | Updated Inventory
Tutor and YP testimonials
| Regular updates of work on soundcloud | 1 update per 8 wk term | 1.e Quality of work being produced by YP is increasing | Recordings of work
| Recordings & perfomances | min. 1 per term |  | Peer Assessment (inc. tutor)
Soundcloud comments
2. To embed learning and effective practice in Host and Partner Orgs (and beyond the programme) | Press releases sent out to relevant journals | Articles in sector newsletters and media | Examples of practice shared through 'AudioActive In The Lab' and Music Education Hub CPD events & publications | Minutes from Hub Meetings
|  | 1 or more citation professional journal | Examples of practice shared/published through professional journals etc | Copy of journals etc
| Posting on YM Network, blogging and creating social media content | min. 2 YM network blogs | Examples and quality of content (and engagement with), blogging and debate posted on YM Network and social media | Screengrabs of content/interactions
| Tweeting and Facebooking | 20 interactions with YM & sector twitter & social media |  | films and video case studies inc. AA Youtube channel
| Follow up with AudioActive In The Lab Event attendees | x consulted | Partners, Practitioners and Young People's perceptions that dissemination is informing practice beyond the programme | Feedback from attendees
| Follow up with delegates of hub training | 4 delegates consulted | Organsiations and practitioners are implementing or planning to implement learning from dissemination. e.g. Increasing YPs use of reflective practice as means to improve the quality of their work | Feedback from Delegates
3. To sustain non-formal music making activity for young people in an otherwise coldspot area | Workshop Blocks | 192 Workshops Oct 2013 Sep 2015 | Sustained provision is ongoing at The School Creative Centre beyond July 2013 | Press & Publicity materials
Screengrabs and links to web content and marketing materials with information of how to get involved
| Fundraising Subcommittee | Fundraising Strategy & Plan | The organisation is attracting funding for ongoing activities from a range of sources (including generated revenue) | Evidence of funding from other sources (offer letters, bank statements)
|  |  | A viable longer term strategy for sustaining activity has been developed and is being implemented | Financial projections copy of strategy for longer term sustainability (inc. fundraising strategy)
4. To increase the number and range of experiences promoting the musical aspirations and development of rurally isolated young people | AudioActive in the Lab Events | 8 x AudioActive in the Lab events | 4a. Increased opportunities for YP to perform their's and see other's work live | photos and video from events survey and debrief feedback
|  | YP sharing contacts for collaborations | 4.bExamples of YP establishing networks and collaborating with others beyond their current networks | case studies Facebook group recordings of Yps collab work The Lab Soundcloud & Comments
|  | Performances from a range of artists beyond current networks | 4.cYP are engaging with more work that inspires them Inc. guest performances at AudioActive In The Lab events | YP testimonials - Surveymonkey
|  | Attendees feedback and video footage of performance | 4d. Examples of YP applying their inspiration to their work/creative process | Tutor testimonials
Examples of YP work e.g. recordings or performance footage
| Workshops including Improvisational | 192 Workshops: Oct 2013 - Sep 2015 | YP are developing transferrable skils e.g. confidence, literacy, recall | Tutor testimonials (je.g through focus groups & Jon clark talking to camera with cutaway of workshop
|  |  | YP's musical ability is increasing | Tutor * YP Testimonials YM Musical Ability Scales
Recordings of improvisational workshops
To increase the use of informal performance and reflective practice as a means for young people to improve the quality of their work | Informal performance & practice sharing events | 8 x AudioActive in the Lab events | 5a.Increased number of opportunities for informal performance and reflective practice | YP Surveys (& Comparison of baseline data with with)
|  |  | 5b.Number of YP engaging in AudioActive In The Lab events | photos and video from events survey and debrief feedback
| De-briefs and reflective practice sessions | 8 x AudioActive In the Lab de-briefs & individual action plans | 5c.Examples of YP developing/refining their work as a result of reflective practice | photos estimated attendance records
|  |  | YP can articulate how AudioActive In The Lab events impact their musical development. | Survey and event debrief feedback video documentation of event debrief examples of work developing throughout project
|  |  | The quality of YP's work is improving throughout the programme | Periodic Examples of YP work e.g. recordings or performance footage
YM Musical Ability Scales
Tutor & YP testimonials (video & focus groups/debriefs)

## Sheet2
Survey Questions
1b | Do you feel that you have a say in the direction of The Lab project
1b | More than before?
4a1 | In the 2 years previous to The Lab how many opportunities did you have to perform?
4c1 | In the 2 years prior to The Lab How many times did you get to see others live performance?
4c2 | Did any of the work you saw at AA in the lab inspire you?
4d | has this impacted your work in any way? How?
5c1 | Did you get any helpful feedback from AA in the lab?
5c2 | What (if anything) do you plan to do with it?
are there artists, genres etc you'd like to see perform at a future AA in the lab?
Do you want to do it again in Bfest?